## Project Plan
Activity Title | Given Earliest Start | Revised Date V2 | Resources | Status | Remarks
Project Initialization
Project Kick of Meeting | 25/08/2016 |  | NSRC, SC
Share Access Control Integration Documents | 28/08/2016 |  | SC
Share the Infrastructure Requirement for Time & Attendance application | 28/08/2016 |  | SC
Provide server instance and infrastructure | 31/08/2016 |  | NSRC
Enabling the server roles (IIS, Web Server, etc) as pre-requsistes on PROD instance | 31/08/2016 |  | SC
Installation of SQL Server 2012-2014 Standard | 31/08/2016 |  | SC
UAT system analysis and database access\module verification | 31/08/2016 |  | SC
Installation of time and attendnace system dependencies (ASP. Net, Crystal Report Run Time, etc) | 01/09/2016 |  | SC
Configuration of service connectors for Access Control Integration | 04/09/2016 |  | SC
Verification of Access Control Data and integration | 04/09/2016 |  | SC
Configuration of integration interfaces for Time & Attendance system | 05/09/2016 |  | SC
Post configuration testing of integration interfaces | 05/09/2016 |  | SC
Business Analysis Phase
Requirement gathering session | 06/09/2016 |  | NSRC, SC
Share HRMS data extract formats and Integration views details | 07/09/2016 |  | SC
Client to share the HRMS data extracts, Oracle views and credentials, Oracle Client Installation and TNS Configuration | 08/09/2016 |  | NSRC
Configure the integration interface with Oracle | 08/09/2016 |  | SC
Implementation Phase
Provide mail server configuratoin and credentials | 11/09/2016 |  | NSRC
Database mail configuration | 12/09/2016 |  | SC
Setup & Configuration (Dashboard, Reports and configurations) | 12/09/2016-13/09/2016 |  | SC
Training
Share the Admin\User Manuals | 14/09/2016 |  | SC
Training Session 1 (Business) | 15/09/2016 |  | NSRC, SC
Training Session 2 (Administration) | 18/09/2016 |  | NSRC, SC
User Acceptance Testing | 19/06/2016 |  | NSRC, SC
Fine tuning and bug fixes | 25/09/2016 |  | SC
UAT signoff | 26/09/2016 |  | NSRC, SC
Go-Live
Integration with BIOSTAR productoin instance and SQL Jobs automation | 26/09/2016 |  | SC
Data reprocessing for 2016 | 27/09/2016 |  | SC
Go-Live Checklist | 28/09/2016 |  | SC
Go-Live | 29/09/2016 |  | NSRC